## Tabelle1
Sprint Review Protocol
Sprint No: |  | 1
Date & Time |  | 2021-04-20 21:00
Group Number |  | 2
Participant 1 |  | Dario Bruckner
Participant 2 |  | Dominik Fohleitner
Participant 3 |  | Amareldo Isufi
Participant 4 |  | Aleksandar Jevtic
Participant 5 |  | Georg Reichert
Mentor |  | Stefan Lackner
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Effort [h] | Delta [h] | Passed | failed | remarks
1 | Movement | 3 | 4 | 1 | 1
2 | Spielerklassen | 15 | 9 | -6 | 1
3 | UI Battle | 9 | 8 | -1 | 1
4 | World | 9 | 8 | -1 | 1
5 | Transition to Battle/World | 3 | 0 | -3 |  | 1 | Battle Mode not ready yet
6 | Work through tutorials | 10 | 20 | 10 | 1
7 |  |  |  | 0
… |  |  |  | 0
… |  |  |  | 0
n |  |  |  | 0
7 |  |  |  | 0 | 5 | 1
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol