## Tabelle1
Sprint Review Protocol
Sprint No: |  | 1
Date & Time |  | 2021-06-21 22:00
Group Number |  | 2
Participant 1 |  | Dario Bruckner
Participant 2 |  | Dominik Fohleitner
Participant 3 |  | Amareldo Isufi
Participant 4 |  | Aleksandar Jevtic
Participant 5 |  | Georg Reichert
Mentor |  | Stefan Lackner
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Effort [h] | Delta [h] | Passed | failed | remarks
1 | Ingame Menu Basic Design | 5 | 8 | 3 | 1
2 | Main Menu Basic Functionality | 5 | 7 | 2 | 1
3 | Unity UI Design Research |  | 3 | 3 | 1
4 | Dynamic World Design | 5 | 8 | 3 | 1
5 | Special Attack/Abilities | 8 | 10 | 2 | 1
6 | Level Up Abilities/Skills | 5 | 5 | 0 | 1
7 | Dynamic Battle UI Design | 5 | 5 | 0 |  | 1
8 | Battle Process Updated |  | 4 | 4 | 1
9 |  |  |  | 0
10 |  |  |  | 0
11 |  |  |  | 0
|  |  | 50 | 17 | 7 | 1
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol