## Tabelle1
Sprint Review Protocol
Sprint No: |  | 1
Date & Time |  | 2021-05-03 21:00
Group Number |  | 2
Participant 1 |  | Dario Bruckner
Participant 2 |  | Dominik Fohleitner
Participant 3 |  | Amareldo Isufi
Participant 4 |  | Aleksandar Jevtic
Participant 5 |  | Georg Reichert
Mentor |  | Stefan Lackner
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Effort [h] | Delta [h] | Passed | failed | remarks
1 | Basic Attack | 2 | 3 | 1 | 1
2 | Basic Heal | 1 | 3 | 2 | 1
3 | Battle System | 3 | 5 | 2 | 1
4 | Character Animation | 2 | 5 | 3 | 1
5 | World design with tilemap | 3 | 3 | 0 | 1
6 | Added Sound and BG music | 2 | 2 | 0 | 1
7 | Transition to Battle | 1 | 2 | 1 | 1
8 | Transition to World | 1 | 1 | 0 | 1
9 | Fixed Superman Jump Bug | 1 | 1 | 0 | 1
10 | Added Enemy to World scene | 2 | 3 | 1
11 | Enemy Classes | 2 | 3 | 1 | 1
|  |  | 31 | 11 | 10 | 0
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol