## Tabelle1
Sprint Review Protocol
Sprint No: |  | 1
Date & Time |  | 2021-05-03 21:00
Group Number |  | 2
Participant 1 |  | Dario Bruckner
Participant 2 |  | Dominik Fohleitner
Participant 3 |  | Amareldo Isufi
Participant 4 |  | Aleksandar Jevtic
Participant 5 |  | Georg Reichert
Mentor |  | Stefan Lackner
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Effort [h] | Delta [h] | Passed | failed | remarks
1 | Added 3 new monsters to the world | 1 | 1 | 0 | 1
2 | New monster animations | 2 | 3 | 1 | 1
3 | added new combat abilities | 3 | 6 | 3 | 1
4 | added new combat mechanics | 3 | 4 | 1 | 1
5 | redefined items in product backlog | 2 | 2 | 0 | 1
6 | created DoR/DoD | 1 | 1 | 0 | 1
7 |  |  |  | 0
8 |  |  |  | 0
9 |  |  |  | 0
10 |  |  |  | 0
11 |  |  |  | 0
|  |  | 17 | 5 | 6 | 0
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol