## Tabelle1
Sprint Review Protocol
Sprint No: |  | 1
Date & Time |  | 2021-07-05 23:00
Group Number |  | 2
Participant 1 |  | Dario Bruckner
Participant 2 |  | Dominik Fohleitner
Participant 3 |  | Amareldo Isufi
Participant 4 |  | Aleksandar Jevtic
Participant 5 |  | Georg Reichert
Mentor |  | Stefan Lackner
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Effort [h] | Delta [h] | Passed | failed | remarks
1 | Display Party stats | 3 | 5 | 2 | 1
2 | Display Item Information | 3 | 5 | 2 | 1
3 | Battleanimations | 3 | 5 | 2 | 1
4 | Loss screen | 1 | 2 | 1 | 1
5 | Win screen | 1 | 2 | 1 | 1
6 | Revive Characters | 3 | 10 | 7 | 1
7 | Using items in Combat | 3 | 10 | 7 | 1
8 | Items Colider and Saving | 1 | 2 | 1 | 1
9 | Relics/Artifacts(logic) | 1 | 2 | 1 | 1
10 | Expand Map | 3 | 5 | 2 | 1
11 | Klassendiagramm | 1 | 1 | 0 | 1
12 | Presentation | 5 | 8 | 3 | 1
13 | Documentation | 5 | 8 | 3 | 1
14 | Bugfixing Battlescene | 0 | 40 | 40 | 1
15 | Bugfixing World | 0 | 20 | 20 | 1
16 | Polishing | 0 | 20 | 20 | 1
|  |  | 145 | 112 | 16 | 0
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol